## Introduction
BlockChain Team Infomation
STT | Member | Student ID | Phone Number | Email | Role
1 | Phạm Nguyễn Gia Bảo | 20127119 | 0926127333 | pngbao20@clc.fitus.edu.vn | Team Leader, Project Manager, software engineer
2 | Nguyễn Minh Hiếu | 21127742 | 0769865503 | Hieu251103@gmail.com | software engineer
3 | Võ Kim Khôi | 22127214 | 848803234 | kimkhoi2004@gmail.com | software engineer
4 | Lê Quốc Khánh | 22127186 | 862933281 | lqkhanh22@clc.fitus.edu.vn | software engineer
5 | Trương Nhật Huy | 22127168 | 0975109887 | truongnhathuy777@gmail.com | software engineer

## Gantt Chart
BlockChain Team Management
PROJECT TITLE | [5 empty] | BlockChain Project | [9 empty] | Group NAME | [9 empty] | Group 2 - HCMUS - BlockChain Subject
PROJECT MANAGER | [5 empty] | Pham Nguyen Gia Bao | [9 empty] | DATE | [9 empty] | 2026-07-08
STT | Thành viên | Tổng trọng số đóng góp | Tổng điểm số đóng góp | Mức độ năng suất | Thứ hạng
1 | Bảo | 1216 | 493 | 0.40543 | 2
2 | Hiếu | 884 | 90 | 0.10181 | 5
3 | Khôi | 1402 | 504 | 0.35949 | 1
4 | Khánh | 1223 | 396 | 0.32379 | 3
5 | Huy | 1015 | 204 | 0.20099 | 4
WBS NUMBER | Tiêu đề nhiệm vụ | Chi tiết nhiệm vụ |  | checklist mục cần hoàn thành, tiêu chí đánh giá | Ghi chú | Người thực hiện | Độ ưu tiên | Độ khó | Ngày bắt đầu | Ngày kết thúc | Thời gian thực hiện | Kết quả thực tế | Mức độ hoàn thành trên checklist yêu cầu thành viên | Trọng số nhiệm vụ | Điểm đóng góp | [12 empty] | PHASE ONE |  | PHASE TWO | [27 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[16 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
 | time axis 2026-07-08 to 2026-09-29
GIAI ĐOẠN 0 — Repository Scaffold
G0 | GIAI ĐOẠN 0 — Repository Scaffold ✅
T0-01 | Tạo cấu trúc thư mục | Tạo src/, tests/, logs/, config/ + __init__.py đúng vị trí; Python package structure hợp lệ |  | src/ tồn tại: 20% tests/ tồn tại: 20% logs/ tồn tại: 20% config/ tồn tại: 20% __init__.py đúng vị trí: 20% |  | Bảo | 9 | 3 | 2026-07-21 | 2026-07-21 | 1 | Cấu trúc thư mục hoàn chỉnh | 100% | 27 | 27
T0-02 | Viết README.md | README.md root: hướng dẫn cài đặt, lệnh test, mô tả dự án + cấu trúc thư mục |  | Hướng dẫn cài đặt: 34% Lệnh chạy test: 33% Mô tả dự án: 33% |  | Bảo | 8 | 2 | 2026-07-21 | 2026-07-21 | 1 | README.md hoàn chỉnh | 100% | 16 | 16
T0-03 | Tạo config/default.json | block_capacity, timeout_schedule (3 loại), retention_policy, network limits — căn cứ PROTOCOL_SPEC.md |  | block_capacity: 25% timeout_schedule: 25% retention_policy: 25% network limits: 25% |  | Bảo | 7 | 4 | 2026-07-21 | 2026-07-21 | 1 | config/default.json đầy đủ | 100% | 28 | 28
T0-04 | Tạo validator_keys.json | 8 cặp khóa Ed25519 deterministic (seed-based HKDF); format {pubkey_hex: privkey_hex}; thứ tự lexicographic |  | 8 cặp key tạo đủ: 50% Seed cố định + thứ tự lexicographic: 50% |  | Bảo | 9 | 6 | 2026-07-21 | 2026-07-21 | 1 | 8 cặp key đã tạo | 100% | 54 | 54
T0-05 | Tạo scenario files | scenario_noop.json, scenario_t1.json, scenario_t8.json; mỗi file có fault_config, network_params, max_height, seed |  | scenario_noop.json: 34% scenario_t1.json: 33% scenario_t8.json: 33% |  | Bảo | 8 | 4 | 2026-07-21 | 2026-07-21 | 1 | 3 scenario files hoàn chỉnh | 100% | 32 | 32
T0-06 | Entry point test + no-op scenario | src/event_log.py (canonical JSONL writer) + src/scenario_runner.py (sim loop) + tests/test_noop.py (3 tests) + tests/verify_determinism.py |  | test_creates_log pass: 25% test_valid_jsonl pass: 25% test_monotonic pass: 25% verify_determinism PASS: 25% | event_log.py và scenario_runner.py implement đầy đủ trong G0 (T0-06 mở rộng) | Bảo | 9 | 8 | 2026-07-21 | 2026-07-21 | 3 | Tất cả tests pass, determinism xác nhận | 100% | 216 | 216
G1 | GIAI ĐOẠN 1 — Primitive Xác Định ✅
T1-01 | encode_uint64 / encode_bool / encode_bytes / encode_str | src/encoding.py — uint64 big-endian 8 bytes, bool 1 byte, bytes với u32 prefix, str NFC+UTF-8 |  | encode_uint64 big-endian: 25% encode_bool 0x01/0x00: 25% encode_bytes u32 prefix: 25% encode_str NFC+UTF-8: 25% | Done — commit 8d5f3e3 | Khánh | 9 | 5 | 2026-07-22 | 2026-07-25 | 1 | Implemented & merged (commit 8d5f3e3) | 100% | 45 | 45
T1-02 | encode_optional_hash | src/encoding.py — presence byte + 32-byte hash; ValueError nếu sai size |  | b"\x00" khi None: 34% b"\x01"+32 bytes: 33% ValueError nếu != 32 bytes: 33% | Done — commit 8d5f3e3 | Khánh | 8 | 4 | 2026-07-22 | 2026-07-25 | 1 | Implemented & merged (commit 8d5f3e3) | 100% | 32 | 32
T1-03 | encode_sorted_map — sorted map encoder | src/encoding.py — sort theo UTF-8 key bytes; format: u64 count ¦¦ encode_bytes(key) ¦¦ encode_bytes(value) |  | Sort UTF-8 key bytes: 34% Prefix u64 count: 33% NFC-normalize key: 33% | Gốc phân cho Huy; Khánh thực hiện gộp trong commit T1-01/02 | Khánh | 8 | 5 | 2026-07-22 | 2026-07-25 | 1 | Implemented & merged (commit 8d5f3e3, Khánh thực hiện) | 100% | 40 | 40
T1-04 | Unit test encoding — 5 hàm + sorted_map | tests/test_encoding.py — test encode_uint64, encode_bool, encode_bytes, encode_str, encode_optional_hash, encode_sorted_map |  | Test encode_sorted_map (3 cases): 40% Test encode_uint64: 15% Test encode_bool: 15% Test encode_bytes: 15% Test encode_optional_hash: 15% | 47 tests pass — tất cả 5 hàm + encode_sorted_map | Huy | 9 | 4 | 2026-07-22 | 2026-07-25 | 1 | 47 tests pass | 100% | 36 | 36
T1-05 | hash_bytes — SHA-256 wrapper | src/crypto.py — hash_bytes(data) -> bytes, trả 32 bytes |  | Import SHA-256: 50% Trả đúng 32 bytes: 50% | 8 tests pass | Khánh | 9 | 3 | 2026-07-22 | 2026-07-25 | 1 | Implemented — 8 tests pass | 100% | 27 | 27
T1-06 | Ed25519 sign() với domain separation | src/crypto.py — sign(privkey, domain, payload): ký utf8(domain) ¦¦ 0x00 ¦¦ payload |  | Concat domain+0x00+payload: 50% Ed25519 sign đúng: 50% | Tests pass | Khôi | 9 | 6 | 2026-07-22 | 2026-07-25 | 1 | Implemented — tests pass | 100% | 54 | 54
T1-07 | Ed25519 verify() với domain separation | src/crypto.py — verify(domain, pubkey, payload, sig): rebuild message rồi verify |  | Rebuild message đúng: 50% Verify signature đúng: 50% | Tests pass | Khôi | 9 | 6 | 2026-07-22 | 2026-07-25 | 1 | Implemented — tests pass | 100% | 54 | 54
T1-08 | Unit test crypto | tests/test_crypto.py — sai domain/key/payload → fail; đúng → pass |  | Sai domain fail: 25% Sai key fail: 25% Sai payload fail: 25% Đúng pass: 25% | 14 tests pass | Hiếu | 9 | 5 | 2026-07-22 | 2026-07-25 | 1 | 14 tests pass | 100% | 45 | 45
T1-09 | Load và validate identity fixtures | src/identity.py — load validator_keys.json, trả về sorted validator list |  | Load file: 34% Validate format: 33% Sorted list: 33% | 10 tests pass | Bảo | 7 | 3 | 2026-07-22 | 2026-07-25 | 1 | 10 tests pass | 100% | 21 | 21
T1-10 | Sorted key-value state map | src/state.py — insert/get/delete; dùng sorted dict đảm bảo thứ tự canonical |  | insert() sorted order: 34% get() đúng: 33% delete() đúng: 33% | src/state.py đầy đủ | Huy | 8 | 5 | 2026-07-22 | 2026-07-25 | 2 | src/state.py đầy đủ — Done | 100% | 80 | 80
T1-11 | State commitment hash | src/state.py — SHA256(encode(entry_count) ¦¦ sorted key-value pairs) |  | encode entry_count: 34% Iterate sorted keys: 33% SHA256 32 bytes: 33% | state_hash() implemented | Huy | 8 | 6 | 2026-07-22 | 2026-07-25 | 1 | state_hash() implemented — Done | 100% | 48 | 48
T1-12 | Transaction object + validation | src/transaction.py — chain_id, nonce, namespace prefix, size limits, signature |  | chain_id: 20% nonce: 20% namespace prefix: 20% size limits: 20% signature: 20% | 8 tests pass | Khánh | 9 | 7 | 2026-07-22 | 2026-07-25 | 2 | 8 tests pass | 100% | 126 | 126
T1-13 | Deterministic executor | src/executor.py — apply tx list → post-state + nonces; invalid tx → invalidate toàn block |  | Apply ordered: 34% Update nonces: 33% Invalid tx → invalidate block: 33% | 22 tests pass (P1 atomicity, P2 determinism, P3 no-double-apply, P4 order) | Khôi | 9 | 8 | 2026-07-22 | 2026-07-25 | 2 | 22 tests pass | 100% | 144 | 144
T1-14 | Unit test determinism executor | tests/test_executor.py — cùng block thực thi 2 lần → byte/hash giống nhau |  | Same post-state hash: 50% Same nonces: 50% | 22 tests pass | Hiếu | 9 | 5 | 2026-07-22 | 2026-07-25 | 1 | 22 tests pass | 100% | 45 | 45
T1-15 | Unit test transaction rejection | tests/test_transaction.py — namespace/nonce/dup/size sai → reject |  | Namespace sai reject: 25% Nonce sai reject: 25% Dup tx reject: 25% Size vượt reject: 25% | 8 tests pass (chuyển từ Hiếu → Bảo) | Bảo | 9 | 5 | 2026-07-22 | 2026-07-25 | 1 | 8 tests pass | 100% | 45 | 45
MGMT | [G1] MG-PR — Review & approve toàn bộ PR giai đoạn 1 | Đọc diff, kiểm tra correctness, canonical sort, test coverage cho tất cả PR G1 |  | Đọc và comment từng PR: 40% Kiểm tra correctness + canonical: 30% Approve/request changes: 30% | Áp dụng G1→G5 (5 × 80 = 400 tổng management PR) | Bảo | 8 | 5 | 2026-07-22 | 2026-07-25 | 2 |  | 0% | 80 | 0
MGMT | [G1] MG-INT — Tích hợp milestone 1 | Merge branches, resolve conflicts, chạy full test suite G1, update trạng thái tài liệu |  | Merge không conflict: 34% Full test suite pass: 33% Update docs trạng thái: 33% | Áp dụng G1→G5 (5 × 28 = 140 tổng management INT) | Bảo | 7 | 4 | 2026-07-22 | 2026-07-25 | 1 |  | 0% | 28 | 0
G2 | GIAI ĐOẠN 2 — Data Model và Xác Thực
T2-01 | Block Header object | src/block.py — fields đúng thứ tự spec; block_hash = SHA256(canonical signed header) |  | Fields đúng thứ tự: 50% block_hash = SHA256: 50% |  | Khánh | 9 | 7 | 2026-07-25 | 2026-07-29 | 2 |  | 100% | 126 | 126
T2-02 | tx_root computation | src/block.py — SHA256(encode(count) ¦¦ tx_id[0] ¦¦ ...); block rỗng = hash(count=0) |  | Tính đúng khi có txs: 50% Block rỗng hash(count=0): 50% |  | Huy | 8 | 5 | 2026-07-25 | 2026-07-29 | 1 |  | 100% | 40 | 40
T2-03 | Header validation guards (F-26) | src/block_validator.py — chain_id, height, round, parent_hash, proposer, HEADER domain sig |  | chain_id: 17% height: 17% round: 16% parent_hash: 17% proposer: 17% HEADER sig: 16% |  | Khôi | 9 | 7 | 2026-07-25 | 2026-07-29 | 2 |  | 100% | 126 | 126
T2-04 | Block Body + candidate validation (F-27–F-29) | src/block.py — tx_root khớp, all txs valid, post-state hash khớp |  | tx_root khớp: 34% All txs valid: 33% post-state hash: 33% |  | Khôi | 9 | 7 | 2026-07-25 | 2026-07-29 | 2 |  | 100% | 126 | 126
T2-05 | Unit test block validation | tests/test_block.py — parent/proposer/height/tx_root/state_hash/sig sai → bắt được |  | parent_hash sai: 17% proposer sai: 17% height sai: 17% tx_root sai: 17% state_hash sai: 16% sig sai: 16% | 35 tests pass (chuyển từ Hiếu → Bảo) | Bảo | 9 | 6 | 2026-07-25 | 2026-07-29 | 1 | 35 tests pass | 100% | 54 | 54
T2-06 | Vote object + validation guards (F-40) | src/vote.py — chain_id, member check, VOTE domain sig, height/round/phase |  | chain_id: 25% member check: 25% VOTE domain sig: 25% height/round/phase: 25% |  | Huy | 8 | 6 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 48 | 0
T2-07 | VoteSet storage | src/vote_set.py — key (height, round, phase, validator_pubkey) |  | Key 4 thành phần: 50% Store/retrieve đúng: 50% |  | Khánh | 8 | 6 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 48 | 0
T2-08 | Duplicate + equivocation detection | src/vote_set.py — duplicate bỏ qua; equivocation log + giữ vote đầu |  | Duplicate bỏ qua: 50% Equivocation log + giữ vote đầu: 50% |  | Khôi | 8 | 7 | 2026-07-25 | 2026-07-29 | 1 |  | 0 | 56 | 0
T2-09 | Quorum counting has_quorum() | src/vote_set.py — True khi >= 2f+1 validators riêng biệt |  | Đếm distinct validators: 50% Ngưỡng 2f+1: 50% |  | Bảo | 9 | 6 | 2026-07-25 | 2026-07-29 | 1 |  | 0 | 54 | 0
T2-10 | Unit test vote_set | tests/test_vote_set.py — duplicate/non-member/equivocation/quorum |  | Duplicate bỏ qua: 25% Non-member từ chối: 25% Equivocation log: 25% Quorum đúng: 25% |  | Hiếu | 9 | 6 | 2026-07-25 | 2026-07-29 | 1 |  | 0 | 54 | 0
T2-11 | Block Store + header-first rule (F-30) | src/block_store.py — store_header(), store_body(); body chỉ sau valid header |  | store_header(): 34% store_body(): 33% Body reject nếu chưa có header: 33% |  | Khôi | 8 | 6 | 2026-07-25 | 2026-07-29 | 1 |  | 0 | 48 | 0
T2-12 | Ledger append-only + snapshot | src/ledger.py — append-only finalized chain + state snapshot; không rollback |  | Chỉ append: 50% State snapshot: 50% |  | Huy | 8 | 7 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 56 | 0
T2-13 | Atomic persist (F-52) | src/ledger.py — ghi nguyên tử finalized_height, finalized_hash, state, nonces, block |  | All-or-nothing: 50% Đủ 5 trường: 50% |  | Hiếu | 9 | 8 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 72 | 0
T2-14 | Crash recovery (F-53) | src/ledger.py — load từ snapshot, discard unfinalized proposals/votes |  | Load snapshot: 50% Discard unfinalized: 50% |  | Khánh | 9 | 8 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 72 | 0
MGMT | [G2] MG-PR — Review & approve toàn bộ PR giai đoạn 2 | Đọc diff, kiểm tra correctness block/vote/ledger logic, test coverage cho tất cả PR G2 |  | Đọc và comment từng PR: 40% Kiểm tra correctness + canonical: 30% Approve/request changes: 30% |  | Bảo | 8 | 5 | 2026-07-25 | 2026-07-29 | 2 |  | 0% | 80 | 0
MGMT | [G2] MG-INT — Tích hợp milestone 2 | Merge branches, resolve conflicts, chạy full test suite G2, update trạng thái tài liệu |  | Merge không conflict: 34% Full test suite pass: 33% Update docs trạng thái: 33% |  | Bảo | 7 | 4 | 2026-07-25 | 2026-07-29 | 1 |  | 0% | 28 | 0
G3 | GIAI ĐOẠN 3 — Mạng Xác Định
T3-01 | Canonical event schema (18 types) | src/event_log.py — 18 event types với fixed field order |  | 18 types đủ: 50% Field order cố định: 50% |  | Khánh | 8 | 5 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 40 | 0
T3-02 | JSON Lines writer canonical | src/event_log.py — fixed key order, no whitespace, UTF-8, newline mỗi event |  | Fixed key order: 25% No whitespace: 25% UTF-8: 25% Newline: 25% |  | Huy | 8 | 5 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 40 | 0
T3-03 | event_no monotonic + logical_time | src/event_log.py — event_no +1 mỗi event; logical_time chính xác |  | event_no +1: 50% logical_time chính xác: 50% |  | Huy | 8 | 4 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 32 | 0
T3-04 | Envelope type | src/network.py — (sender, receiver, payload, logical_time, insertion_seq); serialize đúng |  | Đủ 5 trường: 50% Serialize đúng: 50% |  | Khánh | 7 | 4 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 28 | 0
T3-05 | Deterministic scheduler | src/scheduler.py — priority queue (logical_time, insertion_seq); tie-break insertion_seq |  | Priority queue đúng: 50% Tie-break insertion_seq: 50% |  | Hiếu | 9 | 7 | 2026-07-29 | 2026-08-02 | 2 |  | 0% | 126 | 0
T3-06 | Seeded PRNG | src/scheduler.py — Random(seed) riêng; không dùng random.random() global |  | Random(seed) riêng: 50% Không global random: 50% |  | Khôi | 9 | 6 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 54 | 0
T3-07 | Fault injector | src/fault_injector.py — drop/delay/duplicate/reorder từ config; dùng PRNG T3-06 |  | drop: 25% delay: 25% duplicate: 25% reorder: 25% |  | Khánh | 8 | 7 | 2026-07-29 | 2026-08-02 | 2 |  | 0 | 112 | 0
T3-08 | Bandwidth + rate limiting | src/network.py — bytes/tick không vượt bandwidth_limit_bytes_per_tick |  | Đo bytes/tick: 50% Drop/queue nếu vượt: 50% |  | Hiếu | 6 | 6 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 36 | 0
T3-09 | Peer blocking/unblocking | src/network.py — block_peer() / unblock_peer(); log PEER_BLOCK/PEER_UNBLOCK |  | block_peer + log: 50% unblock_peer + log: 50% |  | Bảo | 6 | 5 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 30 | 0
T3-10 | Canonical iteration order audit | Toàn bộ src/ — sửa mọi dict/set iteration → dùng sorted() |  | No dict iteration: 50% No set iteration: 50% |  | Huy | 9 | 6 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 54 | 0
T3-11 | Message Router | src/router.py — envelope shape, chain_id, sender identity, signature; chỉ tin sig |  | Envelope shape: 25% chain_id: 25% Sender identity: 25% Signature: 25% |  | Khôi | 8 | 7 | 2026-07-29 | 2026-08-02 | 2 |  | 0% | 112 | 0
T3-12 | Router rejection logging | src/router.py — REJECT event với rejection code cho từng guard |  | REJECT event: 50% Code chính xác theo guard: 50% |  | Hiếu | 7 | 5 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 35 | 0
T3-13 | Router drop invalid objects | src/router.py — drop hoàn toàn sau log; không relay invalid |  | Không relay invalid: 50% Log trước drop: 50% |  | Khôi | 8 | 4 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 32 | 0
T3-14 | Scenario Runner chính | src/scenario.py — load config → init nodes → seed PRNG → sim loop → shutdown |  | Load config: 20% Init nodes: 20% Seed PRNG: 20% Sim loop: 20% Shutdown: 20% |  | Khánh | 9 | 8 | 2026-07-29 | 2026-08-02 | 3 |  | 0% | 216 | 0
T3-15 | Ghi spec_version + config_fingerprint | src/scenario.py — spec_version và SHA256(sorted JSON config) vào đầu log |  | spec_version: 50% config_fingerprint SHA256: 50% |  | Hiếu | 7 | 4 | 2026-07-29 | 2026-08-02 | 1 |  | 0 | 28 | 0
T3-16 | Assertion engine safety + liveness | src/scenario.py — safety: không 2 hash cùng height; liveness: height tăng |  | Safety assert: 50% Liveness assert: 50% |  | Khôi | 9 | 7 | 2026-07-29 | 2026-08-02 | 2 |  | 0% | 126 | 0
MGMT | [G3] MG-PR — Review & approve toàn bộ PR giai đoạn 3 | Đọc diff, kiểm tra canonical network/scheduler/router, test coverage cho tất cả PR G3 |  | Đọc và comment từng PR: 40% Kiểm tra correctness + canonical: 30% Approve/request changes: 30% |  | Bảo | 8 | 5 | 2026-07-29 | 2026-08-02 | 2 |  | 0% | 80 | 0
MGMT | [G3] MG-INT — Tích hợp milestone 3 | Merge branches, resolve conflicts, chạy full test suite G3, update trạng thái tài liệu |  | Merge không conflict: 34% Full test suite pass: 33% Update docs trạng thái: 33% |  | Bảo | 7 | 4 | 2026-07-29 | 2026-08-02 | 1 |  | 0% | 28 | 0
G4 | GIAI ĐOẠN 4 — Consensus Engine
T4-01 | ConsensusState per height | src/consensus.py — round, locked_block_hash, locked_round, valid_block_hash, prevotes, precommits |  | Đủ 6 trường: 50% Reset đúng khi height mới: 50% |  | Hiếu | 9 | 8 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 144 | 0
T4-02 | Proposer selection | src/consensus.py — validator_set[sorted][(height+round) % n] |  | Công thức (h+r)%n: 50% Sorted validator set: 50% |  | Khánh | 9 | 5 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 45 | 0
T4-03 | Proposal handler | src/consensus.py — proposer: HEADER trước BODY; non-proposer: timeout → prevote NIL |  | HEADER trước BODY: 50% Timeout → prevote NIL: 50% |  | Khôi | 9 | 8 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 144 | 0
T4-04 | Prevote guard (F-35) | src/consensus.py — unlocked/lock-match → prevote block; quorum later-round → prevote other; else NIL |  | Unlocked prevote block: 34% Lock-match prevote block: 33% Quorum later-round: 33% | Logic phức tạp nhất G4 | Hiếu | 9 | 9 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 162 | 0
T4-05 | Lock logic (F-36) | src/consensus.py — quorum prevote non-NIL → locked_block_hash, locked_round, valid_block_hash |  | Detect quorum non-NIL: 34% locked_block_hash: 33% locked_round+valid_block: 33% |  | Khánh | 9 | 8 | 2026-08-02 | 2026-08-05 | 1 |  | 0 | 72 | 0
T4-06 | Precommit logic (F-37) | src/consensus.py — quorum prevote non-NIL → precommit block; NIL/timeout → precommit NIL |  | Quorum non-NIL → precommit: 50% NIL/timeout → precommit NIL: 50% |  | Khôi | 9 | 8 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 72 | 0
T4-07 | Finalization pipeline (F-38) | src/consensus.py — quorum precommit → revalidate → append ledger → commit state → reset → height+1 |  | Detect quorum: 20% Revalidate: 20% Append ledger: 20% Commit state: 20% Reset+height+1: 20% | Task quan trọng nhất G4 | Huy | 10 | 9 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 180 | 0
T4-08 | Round change (F-39) | src/consensus.py — precommit timeout → round++ → reset vote sets → giữ locks |  | Timeout trigger: 34% Reset vote sets: 33% Giữ locks: 33% |  | Bảo | 9 | 7 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 63 | 0
T4-09 | "Tối đa 1 vote" guard (F-33) | src/consensus.py — enforce per (height, round, phase) — không ký 2 votes cùng phase |  | Track (h,r,phase): 50% Từ chối lần 2: 50% |  | Khánh | 9 | 5 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 45 | 0
T4-10 | Gossip Service | src/gossip.py — sau finalize relay block+votes tới peers; log SEND event |  | Relay block: 50% Log SEND: 50% |  | Huy | 8 | 7 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 112 | 0
T4-11 | Crash simulation | src/scenario.py — dừng node tại logical_time, xóa cache, giữ snapshot; log CRASH |  | Dừng đúng time: 34% Xóa cache: 33% Log CRASH: 33% |  | Hiếu | 8 | 6 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 48 | 0
T4-12 | Restart simulation | src/scenario.py — load snapshot, rebuild consensus state từ gossip; log RESTART |  | Load snapshot: 50% Log RESTART: 50% |  | Khôi | 8 | 7 | 2026-08-02 | 2026-08-05 | 1 |  | 0% | 56 | 0
MGMT | [G4] MG-PR — Review & approve toàn bộ PR giai đoạn 4 | Đọc diff, kiểm tra consensus logic, lock/unlock invariants, test coverage cho tất cả PR G4 |  | Đọc và comment từng PR: 40% Kiểm tra correctness + invariants: 30% Approve/request changes: 30% |  | Bảo | 8 | 5 | 2026-08-02 | 2026-08-05 | 2 |  | 0% | 80 | 0
MGMT | [G4] MG-INT — Tích hợp milestone 4 | Merge branches, resolve conflicts, chạy full test suite G4, update trạng thái tài liệu |  | Merge không conflict: 34% Full test suite pass: 33% Update docs trạng thái: 33% |  | Bảo | 7 | 4 | 2026-08-02 | 2026-08-05 | 1 |  | 0 | 28 | 0
G5 | GIAI ĐOẠN 5 — Test Suite & Nộp Bài
T5-01 | Scenario T1 — Normal run | config/scenario_t1.json + tests/test_t1.py — 8 nodes, no fault, max_height=3 |  | scenario_t1.json: 34% All nodes same height: 33% Same hash+state_hash: 33% |  | Khánh | 9 | 5 | 2026-08-05 | 2026-08-07 | 1 |  | 0% | 45 | 0
T5-02 | Scenario T2 — Duplicate + reorder | config/scenario_t2.json + tests/test_t2.py — inject dup+reorder; vote count đúng, không conflict |  | Inject dup: 34% Vote count đúng: 33% Không conflict: 33% |  | Khánh | 9 | 6 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 54 | 0
T5-03 | Scenario T3 — Bad signature + wrong domain | config/scenario_t3.json + tests/test_t3.py — router từ chối + log; không state transition |  | Router từ chối sai sig: 34% Log REJECT: 33% Không state transition: 33% |  | Hiếu | 9 | 6 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 54 | 0
T5-04 | Scenario T4 — Replay + duplicate tx | config/scenario_t4.json + tests/test_t4.py — tx_id trùng apply tối đa 1 lần |  | Tx_id trùng reject: 50% State reflect 1 lần: 50% |  | Khôi | 9 | 6 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 54 | 0
T5-05 | Scenario T5 — Drop + delay | config/scenario_t5.json + tests/test_t5.py — safety bất biến; không 2 hash cùng height |  | Drop msgs: 34% Delay msgs: 33% Safety: không 2 hash: 33% |  | Huy | 9 | 7 | 2026-08-05 | 2026-08-07 | 2 |  | 0 | 126 | 0
T5-06 | Scenario T6 — Proposer crash | config/scenario_t6.json + tests/test_t6.py — round change xảy ra; proposer khác finalize |  | Proposer crash height 1: 34% Round change: 33% Proposer khác finalize: 33% |  | Huy | 9 | 7 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 63 | 0
T5-07 | Scenario T7 — Equivocation | config/scenario_t7.json + tests/test_t7.py — f=2 conflicting votes; honest nodes không conflict |  | f=2 equivocate: 34% Logged: 33% Honest no conflict: 33% |  | Khôi | 9 | 8 | 2026-08-05 | 2026-08-07 | 2 |  | 0 | 144 | 0
T5-08 | Scenario T8 — Determinism | config/scenario_t8.json + tests/test_t8.py — same seed 2 lần → byte-identical log + state hash |  | Log byte-identical: 50% State hash same: 50% |  | Khánh | 10 | 5 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 50 | 0
T5-09 | Export compact summary | src/summary.py — (height,hash) per node, state hash cuối, rejection counts theo lý do, SHA256 log |  | (height,hash) per node: 25% State hash: 25% Rejection counts: 25% SHA256 log: 25% |  | Hiếu | 7 | 5 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 35 | 0
T5-10 | --verify-determinism script | tests/verify_determinism.py — chạy T8 2 lần, diff log bytes + state hash, exit 0 nếu identical |  | 2 lần cùng seed: 34% Diff log bytes: 33% Exit 0 identical: 33% |  | Bảo | 9 | 4 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 36 | 0
T5-11 | Viết REPORT.pdf | REPORT.pdf — kết quả T1–T8 thực tế, phân tích safety/liveness, <= 10 trang |  | Kết quả T1–T8: 34% Safety analysis: 33% Liveness analysis: 33% |  | Huy | 10 | 5 | 2026-08-05 | 2026-08-07 | 2 |  | 0 | 100 | 0
MGMT | [G5] MG-PR — Review & approve toàn bộ PR giai đoạn 5 | Đọc diff, kiểm tra E2E scenarios, verify determinism pass, test coverage cho tất cả PR G5 |  | Đọc và comment từng PR: 40% Kiểm tra E2E + determinism: 30% Approve/request changes: 30% |  | Bảo | 8 | 5 | 2026-08-05 | 2026-08-07 | 2 |  | 0 | 80 | 0
MGMT | [G5] MG-INT — Tích hợp milestone 5 + đóng gói nộp bài | Merge branches, chạy T1–T8 final, đóng gói ZIP đúng tên nhóm, verify clean checkout |  | T1–T8 all pass: 34% ZIP đúng cấu trúc: 33% Clean checkout verify: 33% |  | Bảo | 7 | 4 | 2026-08-05 | 2026-08-07 | 1 |  | 0 | 28 | 0

## Plan to week9 (85)
BlockChain Team Planning
Tuần | Từ ngày | Đến ngày | Mục tiêu | Công việc tuần | Mức độ hoàn thành